{"text_format":"3","workbook":"xls","n_sheets":4,"sheets":["1.高速公路","2.普通公路","3.港航、枢纽","4.交通执法智能化（其他支撑保障）"],"not_rendered":{"external_links":1,"defined_names":3,"comments":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"1.高速公路","index":0,"n_rows":9,"n_cols":18,"rows_kept":9,"merged":[[0,0,0,16],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[1,5,2,5],[1,6,2,6],[1,7,2,7],[1,8,1,11],[1,12,1,16],[1,17,2,17],[3,0,3,1]],"flags":["formulas_cached_only"]}
["附表1  郁南县高速公路“十四五”规划建设项目表"]
["序号","项目名称","建设性质","建设规模 \n(公里)","计划开工年","计划完工年","总投资\n(亿元)","“十四五”计划投资\n(亿元)","资金来源",{"$nulls":3},"“十四五”各年度计划投资（亿元）",{"$nulls":4},"项目来源"]
[{"$nulls":8},"部省投资(亿元)","市投资(亿元)","县投资(亿元)","其他投资(亿元)","2021年","2022年","2023年","2024年","2025年"]
["“十四五”建设项目合计（2项）储备项目（5项）",null,null,{"v":183.8,"d":"183.80"},null,null,{"v":265.63,"d":"265.6"}]
[1,"G80广昆高速平台出入口","新建","-",2026,2027,{"v":1,"d":"1.0"}]
[2,"S51肇阳高速河口出入口","新建","-",2026,2027,{"v":1,"d":"1.0"}]
[3,"德庆至罗定高速公路德庆至郁南段","新建",{"v":20,"d":"20.00"},2026,2030,{"v":35.33,"d":"35.3"}]
[4,"云浮（郁南）至阳江（阳西）高速公路","新建",{"v":93.8,"d":"93.80"},2026,2030,128.3]
[5,"包茂高速公路广西梧州龙圩至郁南连滩段","新建",{"v":70,"d":"70.00"},2026,2030,{"v":100,"d":"100.0"}]

{"sheet":"2.普通公路","index":1,"n_rows":50,"n_cols":24,"rows_kept":50,"merged":[[0,0,0,21],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,1,8],[1,9,2,9],[1,10,2,10],[1,11,2,11],[1,12,2,12],[1,13,1,16],[1,17,1,21],[1,22,2,22],[3,0,3,1],[4,0,4,1],[6,0,6,1],[7,0,7,1],[15,0,15,1],[22,0,22,1],[24,0,24,1],[28,0,28,1],[29,0,29,1],[41,0,41,1]],"flags":["formulas_cached_only"]}
["附表1 郁南县普通公路“十四五”规划建设项目表"]
["序号","项目名称","建设性质","建设规模 (公里)",{"$nulls":5},"计划开工年","计划完工年","总投资\n(亿元)","“十四五”计划投资\n(亿元)","资金来源",{"$nulls":3},"“十四五”各年度计划投资（亿元）",{"$nulls":4},"项目来源","备注"]
[{"$nulls":3},"一级","二级","三级","四级","桥梁(米)","隧道(米)",{"$nulls":4},"部省投资(亿元)","市投资(亿元)","县投资(亿元)","其他投资(亿元)","2021年","2022年","2023年","2024年","2025年"]
["“十四五”期普通公路建设项目合计（37项）",null,null,{"v":101.884,"d":"101.88"},{"v":89.249,"d":"89.25"},{"v":43.739000000000004,"d":"43.74"},{"v":35.739999999999995,"d":"35.74"},{"v":1980,"d":"1980.00"},{"v":0,"d":"0.00"},null,null,{"v":71.084,"d":"71.08"},{"v":21.234,"d":"21.23"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0.424,"d":"0.42"},{"v":1.3800000000000001,"d":"1.38"},3.04,{"v":7.780000000000001,"d":"7.78"},8.61]
["一、“十四五”期普通国道谋划建设项目（1项）",null,null,50.44,{"$nulls":7},19.02,{"v":0.3,"d":"0.30"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"$nulls":3},{"v":0,"d":"0.00"},{"v":0.3,"d":"0.30"}]
[1,"国道G234郁南县南江口至罗定界段改建工程","改造",50.44,{"$nulls":5},2025,2030,19.02,{"v":0.3,"d":"0.30"},{"$nulls":8},{"v":0.3,"d":"0.30"}]
["二、“十四五”期普通省道建设项目合计（13项）",null,null,{"v":11.443999999999999,"d":"11.44"},45.55,19.87,{"$nulls":5},{"v":37.8,"d":"37.80"},14.13,{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0.3,"d":"0.30"},{"v":0.8500000000000001,"d":"0.85"},2.56,{"v":5.590000000000001,"d":"5.59"},4.83]
["（一）新开工项目（7项）",null,null,{"v":11.443999999999999,"d":"11.44"},45.55,19.87,{"$nulls":5},{"v":14.670000000000002,"d":"14.67"},14.13,{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0.3,"d":"0.30"},{"v":0.8500000000000001,"d":"0.85"},2.56,{"v":5.590000000000001,"d":"5.59"},4.83]
[1,"省道S266线下埇村至广昆高速郁南出口段扩建工程","升级改造、扩建",{"v":6.6,"d":"6.60"},{"$nulls":5},2024,2025,{"v":2.111,"d":"2.11"},{"v":2.111,"d":"2.11"},{"$nulls":7},{"v":1,"d":"1.00"},1.11]
[2,"省道S279线郁南县县城过境路段改线工程","新建",4.844,{"$nulls":5},2023,2024,3.81,3.81,{"$nulls":5},{"v":0.5,"d":"0.50"},{"v":2,"d":"2.00"},1.31,null,"修改"]
[3,"省道 S279 线宝珠大林至黎木根段","升级改造",null,6.47,{"$nulls":4},2021,2023,0.91,0.91,{"$nulls":4},{"v":0.3,"d":"0.30"},{"v":0.3,"d":"0.30"},0.31]
[4,"省道 S279 线宝珠黎木根至大方大塘段路面升级改造工程","升级改造",null,12.38,{"$nulls":4},2024,2025,1.24,1.24,{"$nulls":7},{"v":1,"d":"1.00"},0.24]
[5,"省道 S279 线粟子岗至建城段路面升级改造工程","升级改造",null,{"v":7.4,"d":"7.40"},{"$nulls":4},2025,2026,1.04,{"v":0.5,"d":"0.50"},{"$nulls":8},{"v":0.5,"d":"0.50"}]
[6,"省道S538线大方至通门段新（改）建工程","新（改）建",null,null,19.87,{"$nulls":3},2024,2025,4.98,4.98,{"$nulls":7},{"v":2,"d":"2.00"},2.98]
[7,"省道S538线郁南县佛洞村至东坝镇东坝桥桥头段大修工程","路面改造",null,{"v":19.3,"d":"19.30"},{"$nulls":4},2022,2024,{"v":0.579,"d":"0.58"},{"v":0.579,"d":"0.58"},{"$nulls":5},0.05,0.25,0.28]
["（二）储备项目（6项）",null,null,46.02,111.11,{"$nulls":6},23.13]
[8,"省道S538线郁南县连滩至大方段改造工程","升级改造",null,21.03,{"$nulls":4},2025,2027,{"v":0.6,"d":"0.60"}]
[9,"省道S279线郁南都城镇蟠龙村至蟠龙口段大修工程","路面改造",null,9.27,{"$nulls":4},2025,2026,{"v":1.3,"d":"1.30"}]
[10,"省道 S279 线大方大塘至大湾水口段路面升级改造工程","升级改造",null,{"v":27.1,"d":"27.10"},{"$nulls":4},2026,2027,3.79]
[11,"省道S368线云安交界至都城高岗段路面升级改造工程","升级改造",46.02,{"$nulls":5},2027,2028,{"v":16,"d":"16.00"}]
[12,"省道S538线通门至平台段新（改）建工程","新（改）建",null,46.51,{"$nulls":4},2027,2029,2.33]
[13,"省道S538线郁南县建城至桂圩段改线工程","新建",null,{"v":7.2,"d":"7.20"},{"$nulls":4},2026,2027,1.01]
["三、“十四五”期谋划跨西江大桥重点项目合计（1项）",{"$nulls":6},1800,{"$nulls":3},{"v":2,"d":"2.00"},{"v":0.2,"d":"0.20"},{"$nulls":8},{"v":0.2,"d":"0.20"}]
[1,"郁南都城西江大桥","新建",{"$nulls":4},1800,null,2025,2027,2,{"v":0.2,"d":"0.20"},{"$nulls":8},{"v":0.2,"d":"0.20"},null,"储备项目"]
["四、“十四五”期谋划地方经济及重点网络连接线、旅游公路建设项目合计（3项）",null,null,{"v":40,"d":"40.00"},17.75,{"v":0,"d":"0.00"},{"$nulls":5},9.96,{"v":4.3,"d":"4.30"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":1.5,"d":"1.50"},{"v":2.8,"d":"2.80"}]
[1,"G80连滩出口至S51宋桂出口新建公路","新建",null,17.75,{"$nulls":4},2024,2026,3.96,{"v":3,"d":"3.00"},{"$nulls":7},{"v":1.5,"d":"1.50"},{"v":1.5,"d":"1.50"}]
[2,"都城至连滩一级公路新建工程","新建",{"v":40,"d":"40.00"},{"$nulls":5},2025,2027,{"v":5,"d":"5.00"},{"v":1,"d":"1.00"},{"$nulls":8},{"v":1,"d":"1.00"}]
[3,"郁南县宝珠镇至连滩镇旅游公路","改造",null,null,{"v":30,"d":"30.00"},{"$nulls":3},2025,2027,{"v":1,"d":"1.00"},{"v":0.3,"d":"0.30"},{"$nulls":8},{"v":0.3,"d":"0.30"}]
["五、“十四五”期农村公路建设项目（19项）",{"$nulls":3},{"v":25.949,"d":"25.95"},{"v":23.869,"d":"23.87"},{"v":35.739999999999995,"d":"35.74"},180,{"$nulls":3},{"v":2.3040000000000003,"d":"2.30"},{"v":2.3040000000000003,"d":"2.30"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0.124,"d":"0.12"},0.53,0.48,{"v":0.6900000000000001,"d":"0.69"},0.48]
["（一）新开工项目（11项）",{"$nulls":3},{"v":25.949,"d":"25.95"},{"v":23.869,"d":"23.87"},{"v":35.739999999999995,"d":"35.74"},{"v":180,"d":"180.00"},{"$nulls":3},{"v":2.3040000000000003,"d":"2.30"},{"v":2.3040000000000003,"d":"2.30"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0.124,"d":"0.12"},0.53,0.48,{"v":0.6900000000000001,"d":"0.69"},0.48]
[1,"X417范村至新胜改造工程","改造",null,9.48,4.06,{"$nulls":3},2023,2024,0.27,0.27,{"$nulls":6},{"v":0.2,"d":"0.20"},0.07]
[2,"X466线下咀至思约口段改造工程","升级改造",{"$nulls":3},8.12,null,null,2022,2023,0.15,0.15,{"$nulls":5},{"v":0.1,"d":"0.10"},0.05]
[3,"X467线思约口至石咀段改造工程","升级改造",{"$nulls":3},13.92,null,null,2024,2025,{"v":0.2,"d":"0.20"},{"v":0.2,"d":"0.20"},{"$nulls":7},{"v":0.1,"d":"0.10"},{"v":0.1,"d":"0.10"}]
[4,"X472线大用至历洞段改造工程","路面改造",{"$nulls":3},{"v":13.7,"d":"13.70"},null,null,2024,2025,0.35,0.35,{"$nulls":7},{"v":0.2,"d":"0.20"},0.15]
[5,"X473线栗子岗至桂圩段改造工程","路面改造",null,4.67,{"$nulls":4},2022,2022,0.13,0.13,{"$nulls":5},0.13]
[6,"X473 线桂圩镇过境公路改线工程","新（改）建",null,{"v":1.279,"d":"1.28"},{"$nulls":4},2023,2025,0.48,0.48,{"$nulls":6},0.05,{"v":0.2,"d":"0.20"},0.23]
[7,"X473线罗顺至丁村段大修工程","路面改造",null,{"v":7.4,"d":"7.40"},{"$nulls":4},2022,2022,{"v":0.2,"d":"0.20"},{"v":0.2,"d":"0.20"},{"$nulls":5},{"v":0.2,"d":"0.20"}]
[8,"X480线到角塘至上桥段改造工程","改造",null,null,7.38,{"$nulls":3},2022,2023,0.15,0.15,{"$nulls":5},{"v":0.1,"d":"0.10"},0.05]
[9,"X822逍松线改造工程","改造",null,3.12,{"$nulls":4},2023,2024,0.05,0.05,{"$nulls":6},0.03,0.02]
[10,"Y502水口至双凤单车道改双车道工程","升级改造",null,null,{"v":12.429,"d":"12.43"},{"$nulls":3},"2021","2021",{"v":0.124,"d":"0.12"},{"v":0.124,"d":"0.12"},{"$nulls":4},{"v":0.124,"d":"0.12"}]
[11,"南江口河塱大桥","渡改桥",{"$nulls":4},180,null,2023,2024,{"v":0.2,"d":"0.20"},{"v":0.2,"d":"0.20"},{"$nulls":6},{"v":0.1,"d":"0.10"},{"v":0.1,"d":"0.10"}]
["（二）储备项目（8项）",{"$nulls":3},23.229,53.2,4.64,200,{"$nulls":3},1.6400000000000001,1.6400000000000001,0,0,0,0,null,0.4,0.5,0.64,0.1]
[12,"X474线云霄村至罗定界改造工程","改造",null,null,6.72,{"$nulls":3},2023,2024,{"v":0.1,"d":"0.10"},{"v":0.1,"d":"0.10"},{"$nulls":6},0.05,0.05]
[13,"X474线大湾桥头至五星段改造工程","改造",null,null,2.05,{"$nulls":3},2024,2024,0.04,0.04,{"$nulls":7},0.04]
[14,"X485线宋桂至高村段改造工程","改造",null,8.41,{"$nulls":4},2024,2024,{"v":0.2,"d":"0.20"},{"v":0.2,"d":"0.20"},{"$nulls":7},{"v":0.2,"d":"0.20"}]
[15,"X492线上福至新乐郁南段改造工程","改造",null,null,14.93,{"$nulls":3},2023,2024,{"v":0.3,"d":"0.30"},{"v":0.3,"d":"0.30"},{"$nulls":6},{"v":0.2,"d":"0.20"},{"v":0.1,"d":"0.10"}]
[16,"X801线盛村至凤玉村路面改造工程","改造",null,{"v":6.799,"d":"6.80"},{"$nulls":4},2022,2022,{"v":0.2,"d":"0.20"},{"v":0.2,"d":"0.20"},{"$nulls":5},{"v":0.2,"d":"0.20"}]
[17,"X801线高速出口至朝阳改造工程","改造",null,8.02,null,4.64,null,null,2023,2024,{"v":0.2,"d":"0.20"},{"v":0.2,"d":"0.20"},{"$nulls":6},{"v":0.1,"d":"0.10"},{"v":0.1,"d":"0.10"}]
[18,"X802线古田至大地改造工程","改造",null,null,29.5,{"$nulls":3},2023,2025,0.2,0.2,{"$nulls":6},0.05,0.05,0.1]
[19,"大湾二桥新建工程","新建",{"$nulls":4},200,null,2022,2024,{"v":0.4,"d":"0.40"},{"v":0.4,"d":"0.40"},{"$nulls":5},0.2,0.1,0.1]

{"sheet":"3.港航、枢纽","index":2,"n_rows":15,"n_cols":18,"rows_kept":15,"merged":[[0,0,0,16],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[1,5,2,5],[1,6,2,6],[1,7,2,7],[1,8,1,11],[1,12,1,16],[1,17,2,17],[3,0,3,1],[4,0,4,1],[5,0,5,1],[8,0,8,1],[12,0,12,1],[13,0,13,1]],"flags":["formulas_cached_only"]}
["附表3  郁南县港航、枢纽“十四五”规划建设项目表"]
["序号","项目名称","建设性质","建设规模","开工年","完工年","总投资\n（亿元）","“十四五”计划投资\n(亿元)","资金来源",{"$nulls":3},"“十四五”各年度计划投资（亿元）",{"$nulls":4},"项目来源"]
[{"$nulls":8},"部省投资(亿元)","市投资(亿元)","县投资(亿元)","其他投资(亿元)","2021年","2022年","2023年","2024年","2025年"]
["“十四五”期建设项目合计（6项）",{"$nulls":5},{"v":63.8,"d":"63.80"},23.82,{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0.7,"d":"0.70"},{"v":6.2,"d":"6.20"},{"v":11.6,"d":"11.60"},6.02]
["一、“十四五”期港航建设项目（5项）",{"$nulls":5},{"v":33.8,"d":"33.80"},{"v":23.8,"d":"23.80"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0.7,"d":"0.70"},{"v":6.2,"d":"6.20"},{"v":11.6,"d":"11.60"},{"v":6,"d":"6.00"}]
["（一）新开工建设项目（2项）",{"$nulls":5},{"v":25.3,"d":"25.30"},{"v":22.3,"d":"22.30"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0.7,"d":"0.70"},{"v":6.2,"d":"6.20"},{"v":11.1,"d":"11.10"},{"v":5,"d":"5.00"}]
[1,"建城货运码头","新建","新建15个3000吨级泊位",2022,2025,{"v":23,"d":"23.00"},{"v":20,"d":"20.00"},{"$nulls":5},{"v":0.5,"d":"0.50"},{"v":5,"d":"5.00"},{"v":10,"d":"10.00"},{"v":5,"d":"5.00"}]
[2,"鸿业码头工程","新建","建设3个3000吨级通用泊位（结构按5000吨级预留），码头结构总长300m，码头宽度30m。项目建成后，年件杂货吞吐量为280万吨（其中件杂货220万吨，散货60万吨）。",2022,2024,{"v":2.3,"d":"2.30"},{"v":2.3,"d":"2.30"},{"$nulls":5},{"v":0.2,"d":"0.20"},{"v":1.2,"d":"1.20"},{"v":1.1,"d":"1.10"}]
["（二）谋划建设项目（3项）",{"$nulls":5},{"v":8.5,"d":"8.50"},{"v":1.5,"d":"1.50"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0.5,"d":"0.50"},{"v":0.9999999999999999,"d":"1.00"}]
[3,"新灶口集装箱码头","新建","新建4个3000吨级泊位，占地面积约30万平方米，利用岸线600米，建设进港公路1公里。",2024,2028,{"v":7,"d":"7.00"},{"v":1,"d":"1.00"},{"$nulls":7},{"v":0.3,"d":"0.30"},{"v":0.7,"d":"0.70"}]
[4,"水文化旅游码头","新建","新建2个客位泊位",2024,2026,{"v":0.5,"d":"0.50"},{"v":0.4,"d":"0.40"},{"$nulls":7},{"v":0.2,"d":"0.20"},{"v":0.2,"d":"0.20"}]
[5,"南江口液化天然气（LNG）加注码头","新建","新建2个3000吨级泊位",2025,2027,{"v":1,"d":"1.00"},{"v":0.1,"d":"0.10"},{"$nulls":8},{"v":0.1,"d":"0.10"}]
["二、“十四五”期建设机场枢纽（1项）",{"$nulls":5},{"v":30,"d":"30.00"},0.02,{"$nulls":8},0.02]
["（一）谋划建设项目（1项）",{"$nulls":5},{"v":30,"d":"30.00"},0.02,{"$nulls":8},0.02]
[1,"郁南通用机场","新建","在“十四五”期间配合上级单位完成规划选址。",2025,2030,{"v":30,"d":"30.00"},0.02,{"$nulls":8},0.02]

{"sheet":"4.交通执法智能化（其他支撑保障）","index":3,"n_rows":13,"n_cols":18,"rows_kept":13,"merged":[[0,0,0,16],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[1,5,2,5],[1,6,2,6],[1,7,2,7],[1,8,1,11],[1,12,1,16],[1,17,2,17],[3,0,3,1],[4,0,4,1]],"flags":["formulas_cached_only"]}
["附表4  郁南县交通执法智能化“十四五”规划建设项目表"]
["序号","项目名称","建设性质","建设规模","开工年","完工年","投资情况（亿元）","“十四五”计划投资(亿元)","资金来源",{"$nulls":3},"“十四五”各年度计划投资（亿元）",{"$nulls":4},"项目来源"]
[{"$nulls":8},"部省投资(亿元)","市投资(亿元)","县投资(亿元)","其他投资(亿元)","2021年","2022年","2023年","2024年","2025年"]
["“十四五”期交通执法智能化建设项目合计（8项）",{"$nulls":5},{"v":0.18300000000000002,"d":"0.18"},{"v":0.18300000000000002,"d":"0.18"},{"v":0.07300000000000001,"d":"0.07"},{"v":0.08900000000000001,"d":"0.09"},{"v":0.017,"d":"0.02"},{"v":0,"d":"0.00"},{"v":0.07600000000000001,"d":"0.08"},{"v":0.09000000000000001,"d":"0.09"},{"v":0.017,"d":"0.02"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"}]
["（一）新开工建设项目（8项）",{"$nulls":5},{"v":0.18300000000000002,"d":"0.18"},{"v":0.18300000000000002,"d":"0.18"},{"v":0.07300000000000001,"d":"0.07"},{"v":0.08900000000000001,"d":"0.09"},{"v":0.017,"d":"0.02"},{"v":0,"d":"0.00"},{"v":0.07600000000000001,"d":"0.08"},{"v":0.09000000000000001,"d":"0.09"},{"v":0.017,"d":"0.02"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"}]
[1," 郁南县桂圩治超非现场执法监测点","新建","位于S538线K122+470处，双向两车道加路肩，投资预算170万元，计划于2021年建成。",2021,2021,0.017,0.017,0.017,{"$nulls":3},0.017]
[2,"郁南县平台治超非现场执法监测点","新建","位于S368线K119+400处，双向两车道加路肩，投资预算170万元，计划于2021年建成。",2021,2021,0.017,0.017,0.017,{"$nulls":3},0.017]
[3,"郁南县水口治超非现场执法监测点","新建","位于G234线K3120+400处，双向两车道加路肩，投资预算170万元，计划于2022年建成。",2022,2022,0.017,0.017,null,0.017,{"$nulls":3},0.017]
[4,"郁南县高岗超非现场执法监测点","新建","位于S368线K94+000处，双向四车道加路肩，投资预算340万元，计划于2022年建成。",2022,2022,0.034,0.034,null,0.034,{"$nulls":3},0.034]
[5,"郁南县连滩装卸货场治超非现场执法监测点","新建","位于S368线K119+400处，双向两车道加路肩，投资预算170万元，计划于2023年建成。",2023,2023,0.017,0.017,null,null,0.017,{"$nulls":3},0.017]
[6,"源头治超监控系统","新建","我县目前共有30家源头重点监管企业，计划于2021年先将第一批共10家主要涉及混凝土、石场、矿山、砖厂等企业安装好能连接到县交通运输局监控中心的视频系统，每家企业安装费用预算9万元，监控平台建设100万元，共需投入190万元。2022年计划将剩余20家企业的视频监控系统全部安装完毕，投入费用约180万元。在“十四”五期间，如继续有新增的源头企业，都按要求安装视频监控系统。",2021,2022,0.037,0.037,0.019,0.018,null,null,0.02,0.017]
[7,"治超卸货场的建设","新建","2021年计划建成都城镇治超治卸货场，投入资金约200万元;2022年计划建成宋桂镇治超治卸货场，投入资金约200万元。",2021,2022,0.04,0.04,0.02,0.02,null,null,0.02,0.02]
[8,"交通重点场所的监管系统","新建","在全县重点交通运输场所、集散地安装视频监控系统。2021年计划在都城高铁站、北效车站、原飞凤车站路段安装视频监控，并且将信号连接到县交通运输局监控中心，每个交通监测点计划投入资金5万元，共15万元。2022年计划在南江口高铁站、南江口大桥头、连滩车站、连滩天桥路段、千官车站安装视频监控系统，并且将信号连接到县交通运输局监控中心，每个监测点计划投入建设资金5万元，共需投入25万元.",2021,2022,0.004,0.004,{"$nulls":4},0.002,0.002]