{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["附件2"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"附件2","index":0,"n_rows":6,"n_cols":31,"rows_kept":6,"merged":[[0,0,0,3],[1,0,1,30],[2,0,2,3],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,3,15],[3,16,4,16],[3,17,4,17],[3,18,3,30]],"flags":["formulas_cached_only"]}
["附件2"]
["郁南县新增一般债券资金用途调整明细表"]
["单位（盖章）：郁南县人民政府",{"$nulls":29},"单位：万元"]
["序号","地市","债券全称","发行年度","原项目信息",{"$nulls":11},"调整情形（项目短期内难以继续建设实施/项目实施过程重大变化导致资金需求减少/项目竣工债券资金结余/按照监督检查和审计等意见调整/其他需要调整情形）","调整具体原因","拟调整项目信息"]
[{"$nulls":4},"区划编码","县区","项目名称","项目编码","项目主管部门","项目建设单位","建设状态（未开工/在建/已竣工）","发行时安排债券金额","以前年度是否发生债券资金用途调整（是/否）","本次拟调整用途金额","调整后原项目剩余未使用债券金额","调整后原项目剩余债券资金，预计使用完毕时间（年月）",null,null,"区划编码","县区","项目名称","项目编码","建设状态（未开工/在建/已竣工）","预计竣工日期","以前年度已安排债券资金金额","省政府同意上报申报的2022年一般债券金额","2022年已安排债券资金金额","本次拟安排债券金额","是否属于补办调整手续（即市县已自行调整至该项目使用）（是/否）","预计使用完毕时间（年月）","备注"]
[1,"云浮市","2021年广东省政府一般债券（十三期）","2021年",445322,"郁南县","郁南县2021年小型水库安全运行治理项目","P21445322-0006","郁南县水务局","郁南县水务局","在建",700,"否",302,398,"2022-05-01","项目短期内难以继续建设实施","水库确保春耕用水，导致无法施工",445322,"郁南县","郁南县城基础设施建设和农村教育卫生与安全饮用水扩容提质工程","P20445322-0177","在建","2023-12-01",8000,12000,0,302,"否","2022-05-01"]